## Project Snap Shot
S# | Project(s) Assigned | Project Type | Start Date | End Date
1 | B2software - HOURLY PHP MYSQL |  | 2011-07-21 | 2012-11-28
2 | DWData - LIMEPHP/MYSQL |  | 2012-05-31 | 2013-05-25
3 | ibanklive - developer |  | 2007-08-31 | 2013-08-30
4 | PearInteractive - UAM web project |  | 2012-01-30 | 2012-11-20
5 | SkywardThought : PHP Monthly (beatplay) |  | 2009-12-24 | 2013-04-16
6 | 6th Street - Magento/ CakePHP Monthly |  | 2012-02-16 | 2013-08-29
7 | 6th Street - Designer work 100 hrs/mo. |  | 2012-03-24 | 2013-08-08
8 | 6th Street - Additional PHP Monthly |  | 2012-05-04 | 2013-05-04
9 | Logisticator - INTTRA API integration |  | 2012-05-15 | 2013-05-14
10 | Logisticator - Monthly - oms PHP 2nd dev |  | 2012-05-30 | 2013-05-29
11 | HandMedia ( Magento site edit) |  | 2012-05-01 | 2013-12-26
12 | Emitt Walton Hourly
13 | Imagine8 - Speaker Replay- Simple Replay LAMP 2 MO

## Daily Status Report
S. No | Build Date/ Build No | TestCat Name | Project | Round # | # New issues | # Serious issues | # Re-open bugs | Build Notes | Build Pass | Unit Testing | SVN Tag | Overall Feedback | Time (hrs) | Comment(if any)
1 | 2012-06-18 | PinakiM | DWData - LIMEPHP/MYSQL | R1 | 4 | 0 | 0 | Yes | No | Yes | No | Average | 3 | Tested. 1. Worked on the new modification done by Dev according to client requirement and have sent the status to Dev. 2. Meeting with Dev to understand the previous implemented 'Work Order & Estimate' module.
2 | 2012-06-18 | PinakiM | Technimedia - PHP Backend srvices (Conduct Grader app Development) | R1 | 0 | 0 | 0 | Yes | Yes | Yes | No | Good | 1 | Tested
3 | 2012-06-18 | PinakiM | Utoolize | R1 | 5 | 0 | 0 | Yes | Yes | Yes | No | Good | 3.5 | Tested. The Task for this project was assigned to me by Amit Satpathy.
4 | 2012-06-18 | PinakiM | Other (Meeting) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1.5 | 1. Team Meeting with Amit Satpathy related to project assignment work. 2. Meeting & discussion with Premananda on a new project i.e. Logistic
1 | 2012-06-19 | PinakiM | DWData - LIMEPHP/MYSQL | R2 R1 | 5 | 2 | 1 | Yes | No | Yes | No | Average | 3 hrs | Tested & Reviewed 1. Worked on the new modification done by Dev according to client requirement and have sent the status to Dev. 2. Retested the issues that were raised in last build. 3. Meeting with Dev to understand the previous implemented 'Work Order & Estimate' module.
2 | 2012-06-19 | PinakiM | Technimedia - PHP Backend srvices (Conduct Grader app Development) | R1 | 1 | 0 | 0 | Yes | Yes | Yes | No | Good | 0.75 hrs | Tested
3 | 2012-06-19 | PinakiM | Ibanklive | R1 | 0 | 0 | 0 | Yes | Yes | Yes | No | Good | 2.25 hrs | Tested. There was a small enchancement that was implemented by Dev according to client requirement related to Subscription module which i have tested today. This new implementation works fine with no issues. Note: Please make a note here that this application has some existing bugs for the no of items that were implemented long back. So currently when some requirement comes to me for testing, my main focus is on testing the new functionality that is implemented by Dev according to Client requirement and not on the items that we implemented earlier. I have also informed the development team regrading the existing issues.
4 | 2012-06-19 | PinakiM | CNBC-UAM | R1,R2 | 5 | 0 | 0 | Yes | Yes | Yes | No | Average | 1.5 | Tested. Retested one issues which was failing in IE and tested the new enchancement implemented by Dev, reported issues and have sent the status to Dev.
5 | 2012-06-19 | PinakiM | Other (Meeting) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 1. Team Meeting with Amit Satpathy & Nimmi related to project assignment work. 2. Discussion with Supriti on the DW_Data_LimePHP project status.
1 | 2012-06-20 | PinakiM | DWData - LIMEPHP/MYSQL | R2 R1 | 10 | 2 | 1 (Blocked), 1(Partially fixed) | Yes | No | No | No | Average | 3 hrs | Tested & Reviewed 1. Worked on the new modification by Dev according to client requirement and have sent the status to Dev. 2. Retested the issues that were raised in last build.
2 | 2012-06-20 | PinakiM | Technimedia - 2nd PHP resource ( techinmedia) | R1 | 3 | 1 | 0 | Yes | Yes | Yes | No | Good | 2.5 hrs | Tested. 1. Tested the new implementation according to client requirement and have sent the status report to Dev. Also this new implementation need some more testing after the bugs raised today are fixed.
3 | 2012-06-20 | PinakiM | Ibanklive | R1 | 11 | 0 | 0 | Yes | Yes | Yes | No | Above Average | 3.25 hrs | Tested. 1. Tested the new implementation work sent by client (Email Sub: iBankLive_testing_TVCs Large Preview functionality) 2. Discussion with Dev for understanding the new implementation work.
4 | 2012-06-20 | PinakiM | HandMedia ( Magento site edit) | R1 | 0 | 0 | 0 | Yes | Yes | Yes | No | Average | 1 hrs | Tested. Requirement that I received for this project was very Less. No issue found while testing except few issues which exist in the apps and will discuss the same with Dev_Lead once he is in to office on friday.
5 | 2012-06-20 | PinakiM | Other (Meeting) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1.25 hrs | 1. Team Meeting with Amit Satpathy. 2. Chat with Pankaj and Team 3. Time Spent in composing the DSR report.
1 | 2012-06-22 | PinakiM | DWData - LIMEPHP/MYSQL | R3 | 0 | 0 | 1 | Yes | Yes | Yes | No | Above Average | 4.75 hrs | Reviewed 1. Retested all the issues that we fixed by Dev and have sent the status. 2. Reviewed and retested all the changes in LIVE that we modified this week by dev according to client requirement. (Final testing on Live – All the changes)
2 | 2012-06-22 | PinakiM | Technimedia - 2nd PHP resource ( techinmedia) | R1 R2 | 0 | 0 | 0 | Yes | Yes | Yes | No | Good | 2.25 hrs | Reviewed and Tested. 1. Tested a changes that was sent by client today. 2. Retested all the issues that we reported earlier and were fixed by Dev. 3. Clarified some doubt to dev on the no of issues.
3 | 2012-06-22 | PinakiM | Ibanklive | R2 | 0 | 0 | 0 | Yes | Yes | Yes | No | Average | 1 hrs | Reviewed 1. Retested all the issues that were fixed by Dev and have sent the status.
4 | 2012-06-22 | PinakiM | SkywardThought ( BBBS Site) | R1 | 6 | 0 | 0 | Yes | Yes | Yes | No | Good | 2 hrs | Tested. 1. Tested 2 sections for BBBS site (Home page and all items under About menu). Other task in this project were assigned to another tester (Swarnalipi) for in our team, since she was free (No work assignment) for the day.
5 | 2012-06-22 | PinakiM | Other (DSR Report) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0.75 hrs | 1. Time Spent in composing the DSR report. 2. Time spent in updating the Start/End date of all the project assigned to me in DSR.
1 | 2012-06-25 | PinakiM | DWData - LIMEPHP/MYSQL | R1 | 4 | 3 | 0 | Yes | No | No | No | Poor | 3.5 hrs | Reviewed 1. Tested few new changes that the client has sent this week and have been implemented by Dev. 2. Reported critical issues and have sent the status to dev. Also added a note for the project in GPS. 3. Attended client meeting with Supriti & Developer (Time – 11:55 AM to 12:50 PM).
2 | 2012-06-25 | PinakiM | B2 Software | R3 | 0 | 0 | 0 | Yes | Yes | Yes | No | Good | 4.5 hrs | Reviewed and Tested. 1. Did a 3rd round of testing for reports items since all the blocking issues that were raised earlier were fixed by dev. 2. Retested and closed all the issues that were passing for current/today's build.
3 | 2012-06-25 | PinakiM | SkywardThought ( BBBS Site) | R2 | 0 | 0 | 0 | Yes | Yes | Yes | No | Good | 0.75 hrs | Reviewed 1. Retested all the issues that were fixed by Dev and have sent the status.
4 | 2012-06-25 | PinakiM | Others (Meeting, DSR Report) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1.25 hrs | 1. Time Spent in composing the DSR report. 2. Clarified some doubt to developer of Ibanklive project related to issues. 3. Time spent in submitting the testcat feedback for last week.
1 | 2012-06-26 | PinakiM | DWData - LIMEPHP/MYSQL | R2 | 10 | 3 | 0 | Yes | No | Yes | No | Average | 3 hrs | Tested 1. Worked on and tested the requirement for another project as per email from AmitS and have sent the status to Dev.
2 | 2012-06-26 | PinakiM | PearInteractive - UAM web project | R2, R3 | 1 | 0 | 1 | Yes | Yes | Yes | No | Good | 1.25 hrs | Reviewed 1. Retested all the issues that we fixed by Dev and have sent the status.
3 | 2012-06-26 | PinakiM | 6th Street - Designer work 100 hrs/mo. | R1 | 12 | 0 | 0 | Yes | Yes | Yes | No | Good | 1.5 hrs | Tested 1. Tested the requirement that has been sent by Dev. Basically the requirement for this project was to check content across different browsers (Cross Browser Testng)
4 | 2012-06-26 | PinakiM | Others (Meeting, DSR Report) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1.25 hrs | 1. Team Meeting with Amit Satpathy & Pankaj. 2. Meeting with Supriti and developer for DW-Data-LimePHP project for understanding the new requirement sent by client. 3. Time spent in composing the DSR report.
1 | 2012-06-27 | PinakiM | Data - LIMEPHP/MYSQL | R3 | 0 | 0 | 2 | Yes | No | No | No | Poor | 1.75 hrs | Reviewed 1. Rejected the build for testing since the crasher/error that were reported earlier (Issues ID #53401 & 53571) is still failing if we test these issues by slightly modifying the search query. 2. Meeting/discussion with Pankaj, Amitabh & Supriti on the issues which were still failing for today's build. 3. Discussed with Dev to understand the requirement that needs to be tested.
2 | 2012-06-27 | PinakiM | Handmedia ( Magento site edit) | R1,R2 | 5 | 1 | 1 | Yes | No | Yes | No | Average | 2 hrs (Tested) + 0.75 hrs (Reviewed) = 2.75 hrs | Tested & Reviewed 1. Tested all the new requirement received from Dev. 2. Discussed with Dev to understand the requirement that needs to be tested. 3. Retested all the issues that were fixed by Dev today and have sent the status.
3 | 2012-06-27 | PinakiM | Emitt Walton Hourly | R2 | 0 | 0 | 0 | Yes | Yes | Yes | No | Good | 0.75 hrs | Reviewed 1. Retested all the issues that were fixed by Dev today and have sent the status. 2. Discussed with Dev to understand the requirement that needs to be tested.
4 | 2012-06-27 | PinakiM | Ibanklive | R1,R2 | 1 | 0 | 0 | Yes | Yes | Yes | No | Good | 2.75 hrs (Tested) + 0.5 hrs (Reviewed) = 3.25 hrs | Tested & Reviewed 1. Tested all the new requirement received from Dev. 2. Retested all the issues that were fixed by Dev today and have sent the status. 3. Discussed with Dev to understand the requirement that needs to be tested.
5 | 2012-06-27 | PinakiM | Others (Meeting, DSR Report) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0.25 hrs | 1. Time spent in composing the DSR report.
1 | 2012-06-28 | PinakiM | Emitt Walton Hourly | R1 | 5 | 1 | 0 | Yes | No | No | No | Average | 2.5 hrs | Tested 1. Tested few functionality of the color book apps in android version.
2 | 2012-06-28 | PinakiM | SkywardThought (Beatplay) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3 hrs | Spent some time in going through the site functionality of Beatplay.
3 | 2012-06-28 | PinakiM | Others (Meeting, Chat) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3 hrs | 1. Meeting with Pankaj, Amitabh, Amit & Supriti. 2. QA Team chat in Skype 3. Discussion of DWData-LimePHP & B2software projects status in testcat feedback page in GPS.
1 | 2012-06-29 | PinakiM | B2 Software | R1 | 1 | 0 | 0 | Yes | Yes | Yes | No | Average | 4.25 hrs | Tested 1. Tested the changes/modification sent by client.
2 | 2012-06-29 | PinakiM | Emitt Walton Hourly | R2 | 5 | 2 | 0 | Yes | No | No | No | Average | 1.5 hrs | Tested 1. Tested few functionality of the color book apps in android version. Which were pending yesterday due to unavailability of phone.
3 | 2012-06-29 | PinakiM | 6th Street - Designer work 100 hrs/mo. | R2 | 0 | 0 | 3 | Yes | No | Yes | No | Good | 1.5 hrs | Tested 1. Tested the requirement that has been sent by Dev. Basically the requirement for this project was to check content across different browsers (Cross Browser Testng)
4 | 2012-06-29 | PinakiM | CNBC-UAM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0.5 hrs | 1. Review the new changes/bugs sent by client and have sent a reply to All.
5 | 2012-06-29 | PinakiM | Others (Meeting, Chat) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1.5 hrs | 1. QA Team chat in Skype 2. Spent some time in finding out some info's on the tools sent by Amitabh through email. 3. Spent some time to compose DSR.
1 | 2012-07-02 | PinakiM | Data - LIMEPHP/MYSQL | R1 | 17 | 7 | 0 | Yes | No | No | No | Average | 8 hrs | Tested & Reviewed 1. Tested all the items (change/modification) made by dev according to client instruction. 2. Retested all the issues that were fixed by Dev. 3. Reported new issue in TT found while testing all the items sent by Dev.
2 | 2012-07-02 | PinakiM | Others (Meeting, Chat) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0.75 hrs | 1. Time spent while composing the DSR. 2. Discussed with Dev_Lead (Supriti) on th no of doubt that I had related to items that can to me for test (Project - Data – LIMEPHP/MYSQL)
1 | 2012-07-03 | PinakiM | PearInteractive - UAM web project | R1 | 13 | 3 | 0 | Yes | No | Yes | No | Average | 8.5 hrs | Tested & Reviewed 1. Retesting all the module of this application (Work Status - WIP). Today I have completed 2 modules i.e. Admin module and public pages. The other modules i.e. Leader & Catalyst are still pending to be tested tomorrow. 2. Retested all the client change/issues that were fixed by Dev. 3. Reported new bugs while testing the Admin module and public pages.
2 | 2012-07-03 | PinakiM | Others (Meeting, Chat) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 hrs | 1. Time spent while composing the DSR. 2. Discussed with Dev_Lead (Supriti) and developer on some functionality of UAM Apps.
1 | 2012-07-04 | PinakiM | PearInteractive - UAM web project | R2 | 8 | 2 | 0 | Yes | No | Yes | No | Average | 6.75 hrs | Tested 1. Retesting the modules which were pending to be tested for this application (Work Status - Complete). 2. Reported new bugs while testing the Catalyst/Leader/Applicant modules.
2 | 2012-07-04 | PinakiM | Ibanklive | R1 | 2 | 1 | 0 | Yes | No | Yes | No | Average | 2 hrs | Tested 1. Tested the new changes/modification that we made by Dev according to client requirement. 2. Raised some question/query to Dev_Lead on some items present for subscription. 3. Reported new bugs found for above changes.
3 | 2012-07-04 | PinakiM | Others (Meeting, Chat) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 hrs | 1. Time spent while composing the DSR. 2. Clarified some doubt to Dev on some issues that were reported by me for PearInteractive - UAM web project. 3. Discussion with AmitS on some project related status.
1 | 2012-07-05 | PinakiM | B2Software | R3 | 0 | 0 | 0 | Yes | Yes | Yes | No | Poor | 2 hrs | Reviewed 1. Only reviewed the changes/items that I have tested last week in Live today and verified one issues which was failing in last build.
2 | 2012-07-05 | PinakiM | HandMedia ( Magento site edit) | R1 | 8 | 2 | 0 | Yes | No | No | No | Average | 2.5 hrs | Tested 1. Tested the new changes/modification that we made by Dev according to client requirement. 2. Reported new bugs found while testing the above items.
3 | 2012-07-05 | PinakiM | Logisticator - INTTRA API integration | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 hrs | Meeting and discussion with Dev team for understanding the requirement that I need to test next week.
4 | 2012-07-05 | PinakiM | Others (Meeting, Chat) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3 hrs | 1. Time spent while composing the DSR. 2. Clarified some doubt to Dev on some issues that were reported by me for PearInteractive - UAM web project. 3. Spent some time in preparing the unit testing checklist as per instruction from PankajC and AmitS
1 | 2012-07-06 | PinakiM | B2Software | R1 | 2 | 1 | 0 | Yes | No | No | No | Poor | 1 hrs | Reviewed 1. Tested the new changes implemented by Dev according to client requirement. 2. Reported new bugs found while testing in Team Touch. 3. Skype Call with Dev to understand the requirement before test since the dev was on leave today.
2 | 2012-07-06 | PinakiM | Data - LIMEPHP/MYSQL | R1 | 18 | 6 | 0 | Yes | No | No | No | Average | 6.5 hrs | Tested 1. Tested the new changes implemented by Dev according to client requirement. 2. Reported new bugs found while testing in Team Touch. 3. Discussion with dev on understanding the new requirement.
3 | 2012-07-06 | PinakiM | Others (Meeting, Chat) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1.5 hrs | 1. Time spent while composing the DSR. 2. Submitted Testcat Weekly feedback for all projects. 3. Clarified some doubt on issues to Dev for PearInteractive - UAM web project.
1 | 2012-07-09 | PinakiM | Logisticator - INTTRA API integration | R1 | 15 | 3 | 0 | Yes | Yes | No | No | Average | 6.5 hrs | Tested 1. Tested the new changes implemented by Dev according to client requirement. 2. Reported new bugs found while testing the requirement. 3. Retested the some issues that were found by client and were reported in Mantis bug tracker.
2 | 2012-07-09 | PinakiM | Ibanklive | R1 | 0 | 0 | 0 | Yes | Yes | Yes | No | Good | 1 hrs | Tested 1.Tested a small change/modification done in Edit Subscription page.
3 | 2012-07-09 | PinakiM | SkywardThought ( BBBS Site) | R2 | 0 | 0 | 0 | Yes | Yes | Yes | No | Good | 0.5 hrs | Tested 1. Only tested whether there is any broken link in this site using the Xenu broken link checker tool after theing for this site is pending for requirement were moved to Live server. UI Testing is pending for tomorrow.
4 | 2012-07-09 | PinakiM | Others (Meeting, Chat) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0.5 hrs | 1. Time spent while composing the DSR. 2. Discussion with Developer in understanding the implementation done by them for Logisticator & Ibanklive projects.
1 | 2012-07-10 | PinakiM | SkywardThought (Siti Professional Placement Site) | R1 | 12 | 2 | 0 | Yes | No | No | No | Average | 3.5 hrs | Tested 1. Did a cross browser testing (Live server) on a new site i.e. Siti professional placement under Skyward Thought Project. 2. Reported new bugs found while testing the requirement.
2 | 2012-07-10 | PinakiM | 6th Street - Designer work 100 hrs/mo. | R1 | 3 | 0 | 0 | Yes | No | Yes | No | Good | 0.75 hrs | Tested 1.Tested a template which was designed by Dev to check some UI issues across different browsers.
3 | 2012-07-10 | PinakiM | SkywardThought (BBBS Site) | R3 | 0 | 0 | 0 | Yes | Yes | Yes | No | Good | 3 hrs | Reviewed 1. Reviewed/Cross checked the entire site after the code was moved to Live and have sent the status to Dev.
4 | 2012-07-10 | PinakiM | HandMedia (Magento site edit) | R2 | 0 | 0 | 2 | Yes | No | No | No | Average | 1.25 hrs | Reviewed 1. Retested all the issues that I had reported in the revious build and have sent the status report to dev.
5 | 2012-07-10 | PinakiM | Others (Meeting, Chat) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0.75 hrs | 1. Time spent while composing the DSR. 2. Skype Call with Developer for understanding the project requirements.
1 | 2012-07-11 | PinakiM | 6th Street - Designer work 100 hrs/mo. | R2 | 1 | 0 | 1 (Failed) | Yes | No | Yes | No | Average | 0.5 hrs | Tested/Reviewed 1. Retested all the issues reported in the previous build and reported new issues found in current.
2 | 2012-07-11 | PinakiM | SkywardThought (Siti Professional Placement Site) | R2 | 0 | 0 | 3 (Failed) | Yes | No | Yes | No | Good | 1 hrs | Tested/Reviewed 1. Retested all the issues reported in the previous build.
3 | 2012-07-11 | PinakiM | Data - LIMEPHP/MYSQL | R1 | 7 | 3 | 0 | Yes | No | No | No | Poor | 3.5 hrs | Tested 1. Tested all the requirement for this project sent by dev. 2. Reported all the issues found while testing the requirement.
4 | 2012-07-11 | PinakiM | PearInteractive - UAM web project | R2 | 0 | 0 | 4 | Yes | No | No | No | Average | 2 hrs | Reviewed 1. Retested all the issues that I had reported in the revious build and have sent the status report to dev.
5 | 2012-07-11 | PinakiM | B2 Software | R2 | 0 | 0 | 0 | Yes | Yes | Yes | No | Average | 1 hrs | Tested/Reviewed 1. Tested the reports section which were pending/blocked for test due to the issues that were reported in last build.
6 | 2012-07-11 | PinakiM | Others (Meeting, Chat) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1.5 hrs | 1. Time spent while composing the DSR. 2. QA Team Meeting with AmitS.
1 | 2012-07-12 | PinakiM | HandMedia (Magento site edit) | R3 | 0 | 0 | 0 | Yes | Yes | Yes | No | Average | 0.5 hrs | Reviewed 1. Retested all the issues reported in the previous build.
2 | 2012-07-12 | PinakiM | Data - LIMEPHP/MYSQL | R2 | 1 | 0 | 0 | Yes | No | No | No | Poor | 3.75 hrs | Tested/Reviewed 1. Retested/Reviewed all the issues related to work order section and have sent a status report to Dev team
3 | 2012-07-12 | PinakiM | PearInteractive - UAM web project | R3 | 0 | 0 | 1 | Yes | Yes | Yes | No | Good | 0.5 hrs | Reviewed 1. Retested all the issues reported in the previous build.
4 | 2012-07-12 | PinakiM | B2 Software | R3 | 0 | 0 | 0 | Yes | Yes | Yes | No | Average | 1 hrs | Reviewed 1. Reviewed the changes/modification in Live after the testing the same in Local.
5 | 2012-07-12 | PinakiM | Technimedia Apps | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 hrs | Reviewed 1. Tried to reproduce the issues sent by client. 2. Group discussion with Dev, Dev_Lead related to issues
6 | 2012-07-12 | PinakiM | Others (Meeting, Chat) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1.5 hrs | 1. Time spent while composing the DSR. 2. Spent some time in going through the documents for a new projects i.e. Imagine8 - Speaker Replay- Simple Replay LAMP 2 MO.
1 | 2012-07-13 | PinakiM | HandMedia (Magento site edit) | R1 | 11 | 4 | 0 | Yes | No | No | No | Average | 3 hrs | Tested 1. Tested the new requirement sent by Dev.
2 | 2012-07-13 | PinakiM | Imagine8 - Speaker Replay- Simple Replay LAMP 2 MO | R1 | 7 | 2 | 0 | Yes | No | No | No | Average | 2.5 hrs | Tested 1. Tested the new requirement sent by Dev. 2. Reported new issues in TT
3 | 2012-07-13 | PinakiM | 6th Street - Additional PHP Monthly | R1 | 2 | 0 | 0 | Yes | Yes | Yes | No | Good | 1.5 hrs | Tested 1. Tested the new requirement sent by Dev. 2. Reported new issues and assigned to Dev to fix them.
4 | 2012-07-13 | PinakiM | Data - LIMEPHP/MYSQL | R3 | 0 | 0 | 0 | Yes | No | No | No | Poor | 1 hrs | Reviewed/Tested 1. Tested some items under work order section but this task was paused and has been postpone to monday since the dev was busy with the changes from client that client had sent today and couldn't deliver it to me for test.
5 | 2012-07-13 | PinakiM | Technimedia Apps | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0.75 hrs | Reviewed 1. Retested the issues sent by client.
6 | 2012-07-13 | PinakiM | Others (Meeting, Chat) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0.75 hrs | 1. Time spent while composing the DSR. 2. Discussion with AmitS and Team members on project related task.